## ProjectSchedule (2)
VIVIDLY PROJECT SCHEDULE | [6 empty] | ► Vividly Website
Quegan et al. | Project Start: | 2024-09-01
Project Lead: Jaren Quegan
Members: Jephunneh Jediael Tugas, Stephen Castañeda, & Rovin Navarette |  | 1 |  |  |  | 2024-09-01 | [6 empty] | 2024-09-08 | [6 empty] | 2024-09-15 | [6 empty] | 2024-09-22 | [6 empty] | 2024-09-29 | [6 empty] | 2024-10-06 | [6 empty] | 2024-10-13
 | time axis 2024-09-01 to 2024-10-19
TASK | ASSIGNED TO | START | END | DAYS | DAYS | time axis 2024-09-01 to 2024-10-19
Phase 1 Planning |  |  |  |  | -
Project Team Meeting | All | 2024-09-01 | 2024-09-02 | 2 | 2
Game Mock-ups Creation (including revisions of game mechanics & components) | Quegan | 2024-09-01 | 2024-09-16 | 16 | 16
Game Mechanics reviewed by experts and PWDs |  |  |  |  | -
Phase 2 Game Development
Final Prototype | All | 2024-09-01 | 2024-09-10 | 10
Playtest of the Card Game | All | 2024-09-01 | 2024-09-03 | 3 | 3
Production & Delivery
Phase 3 Implementation
Contacting public and special schools | Quegan | 2024-09-01 | 2024-09-03 | 3 | 3
Workshops | Quegan | 2024-09-01 | 2024-09-04 | 4 | 4
Impact Measurement and Report | Castañeda | 2024-09-01 | 2024-09-01 | 1 | 1
Phase 4 Post-project Review
Team Meeting (Evaluation of Strengths and Areas for Improvement) | Quegan | 2024-09-01 | 2024-09-08 | 8 | 8
2018-01-13
Note on H6: DAYS: This column calculates the duration of the task in calendar days. The duration includes both the Start and End dates.

## ProjectSchedule
VIVIDLY PROJECT SCHEDULE | [7 empty] | ► Vividly Website
Quegan et al. |  | Project Start: | 2023-12-06
Project Lead: Jaren Quegan |  | Today: | 2024-07-27
Members: Jephunneh Tugas, Stephen Castañeda, & Rovin Navarette |  | Display Week: | 1 |  |  |  | 2023-12-03 | [6 empty] | 2023-12-10 | [6 empty] | 2023-12-17 | [6 empty] | 2023-12-24 | [6 empty] | 2023-12-31 | [6 empty] | 2024-01-07 | [6 empty] | 2024-01-14
 | time axis 2023-12-03 to 2024-01-20
TASK | ASSIGNED TO | PROGRESS | START | END | DAYS | DAYS | time axis 2023-12-03 to 2024-01-20
Phase 1 Planning | [5 empty] | -
Brainstorming | All | 100% | 2023-12-06 | 2023-12-11 | 6 | 6
Vision & Strategy | Quegan | 100% | 2023-12-06 | 2023-12-21 | 16 | 16
Phase 2 Reasarch | [5 empty] | -
Conduct Research on Target Beneficiaries | All | 100% | 2023-12-12 | 2023-12-21 | 10 | 10
Analysis of Research Data | All | 100% | 2023-12-22 | 2023-12-24 | 3
Phase 3 Designing/Front-end Development
Create Structure, HTML, JS | Quegan | 100% | 2023-12-24 | 2023-12-26 | 3 | 3
CSS | Quegan | 100% | 2023-12-24 | 2023-12-27 | 4 | 4
Logo Creation | Castañeda | 100% | 2023-12-25 | 2023-12-25 | 1 | 1
Phase 4 Implementation
Implement Logic and System Workflow, Database | Quegan | 100% | 2023-12-28 | 2024-01-04 | 8 | 8
Implement Login, Account Creation, and Password Reset | Quegan | 100% | 2023-12-29 | 2023-12-29 | 1 | 1
Logout Functionality | Quegan | 100% | 2023-12-29 | 2023-12-29 | 1 | 1
User Action (Upload, Edit Posts/Profiles, Follow button etc.) | Quegan | 100% | 2023-12-29 | 2023-12-30 | 2 | 2
Artwork Action (Comments, Like Functionality) | Quegan | 100% | 2023-12-30 | 2023-12-31 | 2 | 2
System Output to User (Link Pages) | Quegan | 100% | 2024-01-01 | 2024-01-01 | 1 | 1
Implement Search Bar | Quegan | 100% | 2024-01-01 | 2024-01-01 | 1 | 1
Implement System Admin | Quegan | 100% | 2024-01-01 | 2024-01-04 | 4 | 4
Phase 5 Testing and Refining
Sample Data Inputs | Tugas | 100% | 2024-01-04 | 2024-01-05 | 2
Test Website Functionality | Quegan | 100% | 2024-01-05 | 2024-01-14 | 10
Identify and Fix Bugs | Quegan | 100% | 2024-01-05 | 2024-01-14 | 10
Phase 6 Preparation
Prepare for Project Presentation | All | 100% | 2024-01-08 | 2024-01-14 | 7
Phase 7 Presentation
Project Proposal | All | 0% | 2024-01-15 | 2024-01-15 | 1
Acknowledge Recommendations | All | 0% | 2024-01-15 | 2024-01-15 | 1
2018-01-13
Note on I6: DAYS: This column calculates the duration of the task in calendar days. The duration includes both the Start and End dates.